## READ ME FIRST
Protected Utility blueprint
Introduction
Document purpose: | The purpose of this document is to capture and assess all of the risks identified in relation to transitioning to the Protected Utility blueprint. In doing so, this document captures and illustrates: - The risks that need to be managed through transition to the blueprint and their severity - The planned treatments and actions for the identified risks Once completed, the findings and insights from the risk assessment will help inform the onwards delivery of the blueprint, and can be used as an input across planning activities, including but not limited to the Transition Plan, Security analysis, Change plan, business readiness plan and business case.
Intended audience: | The intended audience for this document are the agency team members responsible for implementing the blueprint services. This may include: Blueprint project lead and team members Blueprint change team Blueprint communications and engagement team Blueprint training team. Blueprint technical delivery team Agency technology and security team members and stakeholders
Risk sources | The five sources described below may be used to assist in identifying delivery risks.
Risk ratings | Definitions and guidance for rating risks once they have been identified can be found in the 'Risk Rating Matrix' tab of this document.
Risk treatment | The below table provides guidance regarding the appropriate treatment of risks based upon their characteristics. This guidance can be used to support completion of the 'Risk treatment' section of the risk assessment template.

## Risk assessment
Protected Utility blueprint
Legend
Mandatory categories |  | At a minimum., it is recommended that these categories be completed by the Blueprint transition team as part of their assessment |  |  |  |  | Risk rating |  |  | Risk treatment
Optional categories |  | The agency Blueprint transition team may opt to not gather this information as part of their assessment
[7 empty] | Columns I-K will be used to capture the likelihood, impact, and subsequent rating of each risk. The likelihood and impact for each risk should be completed based upon the definitions of the 'Risk Rating Matrix' tab. The risk rating is caculated automatically based upon the likelihood and impact scores for each risk. |  |  | Columns L-P will be used to capture the planned treatment activities for each risk.
Risk ID | Risk Description | Risk status: - Open - Closed | Risk timeframe: - Implementation - Transition - Go-live - Within 3 months of Go-live - Within six months of Go-live | Risk source (e.g. resourcing, technology implementation) | Risk consequences | Existing controls | Risk likelihood | Risk impact | Risk rating | Risk treatment: - Accept - Mitigate - Avoid | Planned actions and mitigations | Responsible officer | Due date | Updates
1 | There is a risk that there may be insufficient time in the delivery plan to transition to the blueprint successfully | Open | Implementation | Planning | Transition to the blueprint is not completed in a timely manner, impacting go-live dates | Detailed project planning and tracking against this plan are in place | Possible | Medium | Moderate | Mitigate | - Continue to track against the plan and impact any slips in activities | J Bloggs | 2021-07-15 | - Risk reviewed 5/7

## Risk Rating Matrix
Protected Utility blueprint
Rating risks
The below matrix is used within the risk assessment workbook as a method for measuring each risk, based upon their likelihood and expected impacts. For example, a risk which has a likelihood of 'possible' and a impact of 'Medium' will receive a rating of 'Moderate'.
Likelihood | Impact
| Insignificant | Minimal | Medium | Major | Severe
Almost Certain | Minor | Moderate | High | Very high | Very high
Likely | Low | Minor | Moderate | High | Very high
Possible | Low | Minor | Moderate | High | Very high
Unlikely | Low | Minor | Moderate | Moderate | High
Rare | Low | Low | Minor | Moderate | High
The below table should be used as a reference for determining the likelihood ratings of risks.
Likelihood rating | Definition
Almost Certain | Expected in most circumstances – 80% or greater probability
Likely | Will probably occur in most circumstances – 50% to 80% probability
Possible | Might occur at some time – 20% to 50% probability
Unlikely | Could occur at some time – 5% to 20% probability
Rare | May occur only in exceptional circumstances – less than 5% probability
The below table should be used as a reference for determining the impact ratings of risks.
Impact rating
Consequence category | Insignificant | Minimal | Medium | Major | Severe
Reputation | One or more project deliverables are unable to meet some of the quality standards in the performance framework | One or more project deliverables are unable to meet all quality standards in performance framework | Branch loses the confidence of the executive | Agency loses the confidence of the government or major stakeholders | Agency abolished or moved back into another agency
Product – user experience | Unavoidable minor impact on user experience | Product does not contribute to improved user experience | Minor negative impacts on user experience or product not tested | Product is boring, complex, slow, frustrating and/or confusing | Product is a barrier to use
People - Health | Minor injury requiring first aid only due to agency negligence | Injury/illness requiring one off minor medical treatment due to agency negligence | Injury/illness requiring ongoing medical treatment due to agency negligence | Fatality or life threatening injury/illness requiring rehabilitation due to agency negligence | WHS incident that means the agency is unable to continue business as usual
Financial & Assets | Less than 1% impact on funding or assets | 1-5% impact on funding or assets | 5%-10% impact on funding or assets | 10%-20% impact on funding or assets | 20% or greater impact on funding or assets
IT Systems & Business Continuity | Isolated internal system/business continuity disruption for <1 hr | Isolated internal system/business continuity disruption for 2 hrs -1 day | Internal system/business outage causing delay to key services for less than 1 day | Full internal system/business outage for 1 day – 1 week | Full internal system/business outage for longer than 1 week
| External platform outage for less than 10 mins | External platforms outage for less than 20 mins | External platforms outage for less than 30 mins | External platforms outage for less than 1 hour | External platforms outage for more than 2 hours
Legislative Compliance | Non-compliance with internal procedures | Non-compliance with internal policy or accidental breach of external requirements | Multiple minor reportable breaches | Multiple cases of non-compliance with legislative requirements | Systematic non-compliance with legislative requirements
Security | Incorrect information supplied to stakeholder | Compromise of confidential or DLM information | Compromise of protected information | Compromise of Secret or small quantities of personal information | Compromise of Top Secret or large quantities of personal information
Privacy | No injury to data subject (no impact on rights and freedoms of individual, employee, third party) | Minor injury to data subjects (limited impact on rights and freedoms of individuals, employees, third parties) | Injuries to data subjects (limited impact on rights and freedoms of individuals, employees, third parties) | Major Injuries to data subjects (high impact on rights and freedoms of individuals, employees, third parties) | Major Injuries to data subjects (high impact on rights and freedoms of individuals, employees, third parties)